## Timeline
Mail METRO MEDIA
Client: | Your Client Name
Campaign Name:
Live Date: | 05/10/2025
Generated: | 13/09/2025
Total Tasks: | 11
Project Duration: | 20 days
Legend:
Client
MMM
Client/Agency
Live Date
Task Name | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5
| Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct
Digital Display - Creative (MMM creating)
Digital Assets sent to MMM | bar: Mon; Sat to Sun
Amendment Approval Phase - 1st Mockup to Client | bar: Mon to Tue; Sat to Sun
Amendment Approval Phase - Client Feedback | bar: Wed; Sat to Sun
test 1 | bar: Thu; Sat to Sun
Amendment Approval Phase - 2nd Mockup to Client | bar: Fri to Sun
Amendment Approval Phase - Client Feedback | bar: Sat to Tue
Amendment Approval Phase - Final Mockup to Client | bar: Sat to Sun; Wed to Thu
Amendment Approval Phase - Client Sign off All creative | bar: Sat to Sun; Fri to Mon
All 3rd Party Tracking sent to MMM | bar: Sat to Sun; Tue
Set Up, Browser Testing, Tagging Implementation, Link Testing | bar: Sat to Sun; Wed to Sun
Live Date | bar: Sat to Sun
Summary
Earliest Start: | Mon: 15/09/2025
Latest End: | Mon: 05/10/2025
Total Working Days: | Mon: 15

## DO_NOT_EDIT_DATA
WARNING: DO NOT OVERWRITE, DO NOT DELETE, DO NOT EDIT - This data is required for timeline import. Modifying this data will prevent the timeline from being imported correctly.
{"version":"2.0.0","exportDate":"2025-09-13T06:14:14.815Z","taskCount":11,"timeline":[{"id":"asset-1757744016561-y8m5j6j1r-template-0","name":"Digital Assets sent to MMM","duration":1,"owner":"c","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[],"start":"2025-09-15","end":"2025-09-15","progress":0,"isCritical":true,"earliestStart":0,"latestStart":0,"startDate":"2025-09-15","endDate":"2025-09-15"},{"id":"asset-1757744016561-y8m5j6j1r-template-1","name":"Amendment Approval Phase - 1st Mockup to Client","duration":2,"owner":"m","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-0","type":"FS","lag":-1}],"start":"2025-09-15","end":"2025-09-16","progress":0,"isCritical":true,"earliestStart":0,"latestStart":0,"startDate":"2025-09-15","endDate":"2025-09-16"},{"id":"asset-1757744016561-y8m5j6j1r-template-2","name":"Amendment Approval Phase - Client Feedback","duration":1,"owner":"c","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-1","type":"FS","lag":0}],"start":"2025-09-17","end":"2025-09-17","progress":0,"isCritical":true,"earliestStart":2,"latestStart":2,"startDate":"2025-09-17","endDate":"2025-09-17"},{"id":"task-1757744041842-4u4vrlt7o","name":"test 1","duration":1,"owner":"a","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":true,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-2","type":"FS","lag":0}],"start":"2025-09-18","end":"2025-09-18","progress":0,"isCritical":true,"earliestStart":3,"latestStart":3,"startDate":"2025-09-18","endDate":"2025-09-18"},{"id":"asset-1757744016561-y8m5j6j1r-template-3","name":"Amendment Approval Phase - 2nd Mockup to Client","duration":1,"owner":"m","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"task-1757744041842-4u4vrlt7o","type":"FS","lag":0}],"start":"2025-09-19","end":"2025-09-19","progress":0,"isCritical":true,"earliestStart":4,"latestStart":4,"startDate":"2025-09-19","endDate":"2025-09-19"},{"id":"asset-1757744016561-y8m5j6j1r-template-4","name":"Amendment Approval Phase - Client Feedback","duration":2,"owner":"c","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-3","type":"FS","lag":0}],"start":"2025-09-22","end":"2025-09-23","progress":0,"isCritical":true,"earliestStart":5,"latestStart":5,"startDate":"2025-09-22","endDate":"2025-09-23"},{"id":"asset-1757744016561-y8m5j6j1r-template-5","name":"Amendment Approval Phase - Final Mockup to Client","duration":2,"owner":"m","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-4","type":"FS","lag":0}],"start":"2025-09-24","end":"2025-09-25","progress":0,"isCritical":true,"earliestStart":7,"latestStart":7,"startDate":"2025-09-24","endDate":"2025-09-25"},{"id":"asset-1757744016561-y8m5j6j1r-template-6","name":"Amendment Approval Phase - Client Sign off All creative","duration":2,"owner":"c","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-5","type":"FS","lag":0}],"start":"2025-09-26","end":"2025-09-29","progress":0,"isCritical":true,"earliestStart":9,"latestStart":9,"startDate":"2025-09-26","endDate":"2025-09-29"},{"id":"asset-1757744016561-y8m5j6j1r-template-7","name":"All 3rd Party Tracking sent to MMM","duration":1,"owner":"a","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-6","type":"FS","lag":0}],"start":"2025-09-30","end":"2025-09-30","progress":0,"isCritical":true,"earliestStart":11,"latestStart":11,"startDate":"2025-09-30","endDate":"2025-09-30"},{"id":"asset-1757744016561-y8m5j6j1r-template-8","name":"Set Up, Browser Testing, Tagging Implementation, Link Testing","duration":3,"owner":"m","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-7","type":"FS","lag":0}],"start":"2025-10-01","end":"2025-10-03","progress":0,"isCritical":true,"earliestStart":12,"latestStart":12,"startDate":"2025-10-01","endDate":"2025-10-03"},{"id":"asset-1757744016561-y8m5j6j1r-template-9","name":"Live Date","duration":1,"owner":"l","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":false,"dependencies":[{"predecessorId":"asset-1757744016561-y8m5j6j1r-template-8","type":"FS","lag":0}],"start":"2025-10-05","end":"2025-10-05","progress":0,"isCritical":true,"earliestStart":15,"latestStart":15,"startDate":"2025-10-05","endDate":"2025-10-05"}],"selectedAssets":[{"id":"asset-1757744016561-y8m5j6j1r","type":"Digital Display - Creative (MMM creating)","name":"Digital Display - Creative (MMM creating)","startDate":"2025-10-05"}],"globalLiveDate":"2025-10-05","assetLiveDates":{},"useGlobalDate":true,"customTasks":[{"id":"task-1757744041842-4u4vrlt7o","name":"test 1","duration":1,"owner":"a","assetId":"asset-1757744016561-y8m5j6j1r","assetType":"Digital Display - Creative (MMM creating)","isCustom":true,"insertAfterTaskId":"asset-1757744016561-y8m5j6j1r-template-2"}],"assetTaskDurations":{},"customTaskNames":{}}